## Instructions
Background
The purpose of this tool is to assist the team in determining the project's health and the team's performance. In a Scrum context we measure health by using Burndown charts, Burnup charts and tracking Created vs Resolved bugs. To track team performance we use Velocity Charts in story points. This spreadsheet will provide the team with additional tools to help facilite discussions around increasing flow efficiency through the Kanban board, help improve the predictability of work scheduled for future sprints and visualize team performance using throughput (Stories completed per time period).
How to use this tool
The cells that require input from the team will have a white background. The following section will describe how to do to use it.
Setup
1) Fill in the Holidays for the project in the Lookup Tables Sheet.
2) In the Aging WIP Sheet enter in the date of the first day of the project in Cell A2
3) In the Throughput Sheet enter in the date of the first Friday of the project.
Tracking Stories
On the Stories Sheet the Lead Time is calculated by using the Start date and End date of a Story. To track stories enter the following informaiton for each story:
1) Story ID (JIRA, TFS or made up)
2) Start Date - date the story was pulled into development
3) End Date - date the story was set to done or closed
4) Story Points - If applicable, the effort of that story as a number
5) The Waiting Time of that Story. One way to do this is draw a dot on the Sticky on the Kanban board for each day the Story that is in dev or test but is not being activley worked on.
Tracking Bugs
To Track Bugs create a copy of this workbook and enter bug ticket information in the Stories WorkSheet. I would not recommend miiing Bugs and Stories data in the same WorksheetT. he lead time disttribution will be different between the two types of work.
Tracking Increased Understanding, Scope Creep, Discovered Work etc.
The Dark Matter Sheet is used to track discovered work. This sheet will track discovered work a high level story grouping such as a Feature/Epic/Activity level (Think story map Activity/User Task/Detail). At some point before development work is broken down into User Stories, when that happens record the count of stories for that grouping as the Original # of stories. During development if work is discovered, stories are split, or the client asked for additional work keep track of which grouping those addiational stories fall under. When the Feature/Epic/Activity is complete, count the number of stories and record it in the Current # of Stories column. This data can be used to forecast future work.
Tracking Project Buffer (Experimental)
Typically on a project there is some sort of Ramp up period and ramp down period. Work can generally be plotted in a Z curve (see example to the right). Where the first and third sections of the Z curve work flows more slowly than the middle section.
The "Project Buffer" is based off a model created by Dimitar Bakardzhiev. The model calculates an appropriate "project buffer" based on three calibarated estimates:
Z-curve coefficient - This is the % of total project time spent on ramp up and ramp down.
Average Failure Demand - expressed as a percentage. This is the rate of failures in the system (bugs, tech debt, rework)
Average Dark Matter - expressed as a percentage. This is the rate of work expansion (scope creep, increased understanding).
To use this Spreadsheet enter the Total Bugeted Stories, Estimated average Throughput (per week), and the three estimates listed above.
Note: This is an idea I pulled directly from the book Scrumban Revolution by Ajay Reddy and I am still trying to get a better understanding of it.

## Stories
ID | Start Date | Closed Date | Effort (Story Points) | Waiting Time | Lead Time (Days) | Running Average Lead Time | Flow Efficiency
132456 | 2015-06-21 | 2015-07-14 | 5 |  | 7 | 7 | 100
2
1
1
1
1
5
20
20
21
20
20
20
20
20
20
20
20
1
1
Formulas:
Lead Time (Days) = IF(ISBLANK([Start Date]), "", IF(ISBLANK([Closed Date]),NETWORKDAYS([Start Date],TODAY(), Holidays),NETWORKDAYS([Start Date],[Closed Date], Holidays)))
The darker gray areas are caluclated fields. This use this spreadsheet put the following in for each Story (ticket or whatever you call it).
ID is the ID in JIRA or TFS or whatever you are using
Start Date is the date the story is pulled into development
End Date is the date the story leaves test (set to done or closed)
Effort is in story points
Waiting Time is the time that the story is in development but not activly being worked on. This includes blocks, extra long wait to get reviewed, stuck in test ready.
Lead Time is the End Date - Start Date
Flow Efficiency is used to determine if there is waste in the system. Ideally you would not want the story waiting at all during development. so 100% flow effieciecy is a good goal

## Story-Statistics
Bin | Frequency of Cycle Times | Cumulative %
1 | 0 | 0
2 | 0 | 0
3 | 0 | 0 | Max | 7
4 | 0 | 0 | Min | 7
5 | 0 | 0 | Median | 7
6 | 0 | 0 | Average | 7
7 | 1 | 100 | 5th Percentile | 7
8 | 0 | 100 | 95th Percentile | 7
9 | 0 | 100
10 | 0 | 100
11 | 0 | 100
12 | 0 | 100
13 | 0 | 100
14 | 0 | 100
15 | 0 | 100
16 | 0 | 100
17 | 0 | 100
18 | 0 | 100
19 | 0 | 100
20 | 0 | 100
More than 20 | 0 | 100
This is inspired by the tool Kanban Sim. This distribution helps visualize the variability the lead times for each story. Wider distributions for data typically signal greater variabiltiy and lower predictability.
Use the 5th and 95th percentile for Lead time ranges in you Kanban Sim models.

## Aging WIP
Date | WIP | Average WIP | Average Lead Time | Stories Closed | Average Throughput | Calcuated Lead Time (Little's Law)
2015-03-12 | 0 | 0 |  | 0 | 0
2015-03-13 | 0 | 0 |  | 0 | 0
2015-03-16 | 0 | 0 |  | 0 | 0
2015-03-17 | 0 | 0 |  | 0 | 0
2015-03-18 | 0 | 0 |  | 0 | 0
2015-03-19 | 0 | 0 |  | 0 | 0
2015-03-20 | 0 | 0 |  | 0 | 0
2015-03-23 | 0 | 0 |  | 0 | 0
2015-03-24 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-03-25 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-03-26 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-03-27 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-03-30 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-03-31 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-01 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-02 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-03 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-06 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-07 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-08 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-09 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-10 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-13 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-14 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-15 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-16 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-17 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-20 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-21 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-22 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-04-23 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | Bin | Frequency | Cumulative %
2015-04-24 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 1 | 6 | 4.32
2015-04-27 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 2 | 0 | 4.32
2015-04-28 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 3 | 0 | 4.32
2015-04-29 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 4 | 0 | 4.32
2015-04-30 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 5 | 0 | 4.32
2015-05-01 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 6 | 0 | 4.32
2015-05-04 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 7 | 0 | 4.32
2015-05-05 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 8 | 0 | 4.32
2015-05-06 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 9 | 0 | 4.32
2015-05-07 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 10 | 0 | 4.32
2015-05-08 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 11 | 0 | 4.32
2015-05-11 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 12 | 0 | 4.32
2015-05-12 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 13 | 0 | 4.32
2015-05-13 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 14 | 0 | 4.32
2015-05-14 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 15 | 0 | 4.32
2015-05-15 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 16 | 0 | 4.32
2015-05-18 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 17 | 0 | 4.32
2015-05-19 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 18 | 0 | 4.32
2015-05-20 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 19 | 0 | 4.32
2015-05-21 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 20 | 0 | 4.32 | Max | 1
2015-05-22 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 21 | 0 | 4.32 | Min | 0
2015-05-25 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 22 | 0 | 4.32 | Median | 0
2015-05-26 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 23 | 0 | 4.32 | Average | 0.043165
2015-05-27 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 24 | 0 | 4.32 | 5th Percentile | 0
2015-05-28 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 25 | 0 | 4.32 | 95th Percentile | 0
2015-05-29 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 26 | 0 | 4.32
2015-06-01 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 27 | 0 | 4.32
2015-06-02 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 28 | 0 | 4.32
2015-06-03 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 29 | 0 | 4.32
2015-06-04 | 0 | 0 | #N/A | 0 | 0 | #DIV/0! | 30 | 0 | 4.32
2015-06-05 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-06-08 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-06-09 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-06-10 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-06-11 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-06-12 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-06-15 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-06-16 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-06-17 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-06-18 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-06-19 | 0 | 0 | #N/A | 0 | 0 | #DIV/0!
2015-07-06 | 1 | 0.013699 | #N/A | 0 | 0 | #DIV/0!
2015-07-07 | 1 | 0.027027 | #N/A | 0 | 0 | #DIV/0!
2015-07-08 | 1 | 0.04 | #N/A | 0 | 0 | #DIV/0!
2015-07-09 | 1 | 0.052632 | #N/A | 0 | 0 | #DIV/0!
2015-07-10 | 1 | 0.064935 | #N/A | 0 | 0 | #DIV/0!
2015-07-13 | 1 | 0.076923 | #N/A | 0 | 0 | #DIV/0!
2015-07-14 | 0 | 0.075949 | 7 | 1 | 0.012658 | 6
2015-07-15 | 0 | 0.075 | 7 | 0 | 0.0125 | 6
2015-07-16 | 0 | 0.074074 | 7 | 0 | 0.012346 | 6
2015-07-17 | 0 | 0.073171 | 7 | 0 | 0.012195 | 6
2015-07-20 | 0 | 0.072289 | 7 | 0 | 0.012048 | 6
2015-07-21 | 0 | 0.071429 | 7 | 0 | 0.011905 | 6
2015-07-22 | 0 | 0.070588 | 7 | 0 | 0.011765 | 6
2015-07-23 | 0 | 0.069767 | 7 | 0 | 0.011628 | 6
2015-07-24 | 0 | 0.068966 | 7 | 0 | 0.011494 | 6
2015-07-27 | 0 | 0.068182 | 7 | 0 | 0.011364 | 6
2015-07-28 | 0 | 0.067416 | 7 | 0 | 0.011236 | 6
2015-07-29 | 0 | 0.066667 | 7 | 0 | 0.011111 | 6
2015-07-30 | 0 | 0.065934 | 7 | 0 | 0.010989 | 6
2015-07-31 | 0 | 0.065217 | 7 | 0 | 0.01087 | 6
2015-08-03 | 0 | 0.064516 | 7 | 0 | 0.010753 | 6
2015-08-04 | 0 | 0.06383 | 7 | 0 | 0.010638 | 6
2015-08-05 | 0 | 0.063158 | 7 | 0 | 0.010526 | 6
2015-08-06 | 0 | 0.0625 | 7 | 0 | 0.010417 | 6
2015-08-07 | 0 | 0.061856 | 7 | 0 | 0.010309 | 6
2015-08-10 | 0 | 0.061224 | 7 | 0 | 0.010204 | 6
2015-08-11 | 0 | 0.060606 | 7 | 0 | 0.010101 | 6
2015-08-12 | 0 | 0.06 | 7 | 0 | 0.01 | 6
2015-08-13 | 0 | 0.059406 | 7 | 0 | 0.009901 | 6
2015-08-14 | 0 | 0.058824 | 7 | 0 | 0.0098039 | 6
2015-08-17 | 0 | 0.058252 | 7 | 0 | 0.0097087 | 6
2015-08-18 | 0 | 0.057692 | 7 | 0 | 0.0096154 | 6
2015-08-19 | 0 | 0.057143 | 7 | 0 | 0.0095238 | 6
2015-08-20 | 0 | 0.056604 | 7 | 0 | 0.009434 | 6
2015-08-21 | 0 | 0.056075 | 7 | 0 | 0.0093458 | 6
2015-08-24 | 0 | 0.055556 | 7 | 0 | 0.0092593 | 6
2015-08-25 | 0 | 0.055046 | 7 | 0 | 0.0091743 | 6
2015-08-26 | 0 | 0.054545 | 7 | 0 | 0.0090909 | 6
2015-08-27 | 0 | 0.054054 | 7 | 0 | 0.009009 | 6
2015-08-28 | 0 | 0.053571 | 7 | 0 | 0.0089286 | 6
2015-08-31 | 0 | 0.053097 | 7 | 0 | 0.0088496 | 6
2015-09-01 | 0 | 0.052632 | 7 | 0 | 0.0087719 | 6
2015-09-02 | 0 | 0.052174 | 7 | 0 | 0.0086957 | 6
2015-09-03 | 0 | 0.051724 | 7 | 0 | 0.0086207 | 6
2015-09-04 | 0 | 0.051282 | 7 | 0 | 0.008547 | 6
2015-09-07 | 0 | 0.050847 | 7 | 0 | 0.0084746 | 6
2015-09-08 | 0 | 0.05042 | 7 | 0 | 0.0084034 | 6
2015-09-09 | 0 | 0.05 | 7 | 0 | 0.0083333 | 6
2015-09-10 | 0 | 0.049587 | 7 | 0 | 0.0082645 | 6
2015-09-11 | 0 | 0.04918 | 7 | 0 | 0.0081967 | 6
2015-09-14 | 0 | 0.04878 | 7 | 0 | 0.0081301 | 6
2015-09-15 | 0 | 0.048387 | 7 | 0 | 0.0080645 | 6
2015-09-16 | 0 | 0.048 | 7 | 0 | 0.008 | 6
2015-09-17 | 0 | 0.047619 | 7 | 0 | 0.0079365 | 6
2015-09-18 | 0 | 0.047244 | 7 | 0 | 0.007874 | 6
2015-09-21 | 0 | 0.046875 | 7 | 0 | 0.0078125 | 6
2015-09-22 | 0 | 0.046512 | 7 | 0 | 0.0077519 | 6
2015-09-23 | 0 | 0.046154 | 7 | 0 | 0.0076923 | 6
2015-09-24 | 0 | 0.045802 | 7 | 0 | 0.0076336 | 6
2015-09-25 | 0 | 0.045455 | 7 | 0 | 0.0075758 | 6
2015-09-28 | 0 | 0.045113 | 7 | 0 | 0.0075188 | 6
2015-09-29 | 0 | 0.044776 | 7 | 0 | 0.0074627 | 6
2015-09-30 | 0 | 0.044444 | 7 | 0 | 0.0074074 | 6
2015-10-01 | 0 | 0.044118 | 7 | 0 | 0.0073529 | 6
2015-10-02 | 0 | 0.043796 | 7 | 0 | 0.0072993 | 6
2015-10-05 | 0 | 0.043478 | 7 | 0 | 0.0072464 | 6
2015-10-06 | 0 | 0.043165 | 7 | 0 | 0.0071942 | 6
Formulas:
Date = WORKDAY([Date, row above], 1, Holidays)
Aging WIP indicates whether flow is stable or stationary far in advance of lead time. Whenever the average lead time of the daily output is less than the nominal lead time from the system (average perdicted under Little's law), then the system's WIP is aging.
Note on E2: Robert M. Nowadly: Try converting this to a sum product thing

## Throughput
Date | Stories Complete
2015-03-06 | 0
2015-03-20 | 0
2015-03-27 | 0
2015-04-03 | 0
2015-04-10 | 0
2015-04-17 | 0 | Max | 1
2015-04-24 | 0 | Min | 0
2015-05-01 | 0 | Median | 0
2015-05-08 | 0 | Average | 0.038462
2015-05-15 | 0 | 5th Percentile | 0
2015-05-22 | 0 | 95th Percentile | 0
2015-05-29 | 0
2015-06-05 | 0
2015-06-12 | 0
2015-06-19 | 0
2015-07-10 | 0
2015-07-17 | 1
2015-07-24 | 0
2015-07-31 | 0
2015-08-07 | 0
2015-08-14 | 0
2015-08-21 | 0
2015-08-28 | 0
2015-09-04 | 0
2015-09-11 | 0
2015-09-18 | 0
Throughput in this graph is how many stories were completed in a week. An increase in thoughput may be the result of some improvemnet made by the team to eliminate waste.

## Pts vs Lead Time
7
#VALUE!
This is a correlation between Story Point estimate and actual lead times in days. In theory, the higher the story point value the higher the lead time.

## Dark Matter
Epic / Activity Name | Original # of Stories | Current # of Stories | % Difference | Bin | % Difference Frequency | Cumulative %
Activity A | 100 | 150 | 50 | 1 | 0 | 0
Activity B | 150 | 300 | 100 | 2 | 0 | 0
Activity C | 75 | 85 | 13 | 3 | 0 | 0 | Max | 100
|  |  |  | 4 | 0 | 0 | Min | 13
|  |  |  | 5 | 0 | 0 | Median | 50
|  |  |  | 6 | 0 | 0 | Average | 54.3333
|  |  |  | 7 | 0 | 0 | 5th Percentile | 16.7
|  |  |  | 8 | 0 | 0 | 95th Percentile | 95
|  |  |  | 9 | 0 | 0
|  |  |  | 10 | 0 | 0
|  |  |  | 11 | 0 | 0
|  |  |  | 12 | 0 | 0
|  |  |  | 13 | 1 | 33.33
|  |  |  | 14 | 0 | 33.33
|  |  |  | 15 | 0 | 33.33
|  |  |  | 16 | 0 | 33.33
|  |  |  | 17 | 0 | 33.33
|  |  |  | 18 | 0 | 33.33
|  |  |  | 19 | 0 | 33.33
|  |  |  | 20 | 0 | 33.33
|  |  |  | 21 | 0 | 33.33
|  |  |  | 22 | 0 | 33.33
|  |  |  | 23 | 0 | 33.33
|  |  |  | 24 | 0 | 33.33
|  |  |  | 25 | 0 | 33.33
|  |  |  | 26 | 0 | 33.33
|  |  |  | 27 | 0 | 33.33
|  |  |  | 28 | 0 | 33.33
|  |  |  | 29 | 0 | 33.33
|  |  |  | 30 | 0 | 33.33
|  |  |  | 31 | 0 | 33.33
|  |  |  | 32 | 0 | 33.33
|  |  |  | 33 | 0 | 33.33
|  |  |  | 34 | 0 | 33.33
|  |  |  | 35 | 0 | 33.33
|  |  |  | 36 | 0 | 33.33
|  |  |  | 37 | 0 | 33.33
|  |  |  | 38 | 0 | 33.33
|  |  |  | 39 | 0 | 33.33
|  |  |  | 40 | 0 | 33.33
|  |  |  | 41 | 0 | 33.33
|  |  |  | 42 | 0 | 33.33
|  |  |  | 43 | 0 | 33.33
|  |  |  | 44 | 0 | 33.33
|  |  |  | 45 | 0 | 33.33
|  |  |  | 46 | 0 | 33.33
|  |  |  | 47 | 0 | 33.33
|  |  |  | 48 | 0 | 33.33
|  |  |  | 49 | 0 | 33.33
|  |  |  | 50 | 1 | 66.66
|  |  |  | 51 | 0 | 66.66
|  |  |  | 52 | 0 | 66.66
|  |  |  | 53 | 0 | 66.66
|  |  |  | 54 | 0 | 66.66
|  |  |  | 55 | 0 | 66.66
|  |  |  | 56 | 0 | 66.66
|  |  |  | 57 | 0 | 66.66
|  |  |  | 58 | 0 | 66.66
|  |  |  | 59 | 0 | 66.66
|  |  |  | 60 | 0 | 66.66
|  |  |  | 61 | 0 | 66.66
|  |  |  | 62 | 0 | 66.66
|  |  |  | 63 | 0 | 66.66
|  |  |  | 64 | 0 | 66.66
|  |  |  | 65 | 0 | 66.66
|  |  |  | 66 | 0 | 66.66
|  |  |  | 67 | 0 | 66.66
|  |  |  | 68 | 0 | 66.66
|  |  |  | 69 | 0 | 66.66
|  |  |  | 70 | 0 | 66.66
|  |  |  | 71 | 0 | 66.66
|  |  |  | 72 | 0 | 66.66
|  |  |  | 73 | 0 | 66.66
|  |  |  | 74 | 0 | 66.66
|  |  |  | 75 | 0 | 66.66
|  |  |  | 76 | 0 | 66.66
|  |  |  | 77 | 0 | 66.66
|  |  |  | 78 | 0 | 66.66
|  |  |  | 79 | 0 | 66.66
|  |  |  | 80 | 0 | 66.66
|  |  |  | 81 | 0 | 66.66
|  |  |  | 82 | 0 | 66.66
|  |  |  | 83 | 0 | 66.66
|  |  |  | 84 | 0 | 66.66
|  |  |  | 85 | 0 | 66.66
|  |  |  | 86 | 0 | 66.66
|  |  |  | 87 | 0 | 66.66
|  |  |  | 88 | 0 | 66.66
|  |  |  | 89 | 0 | 66.66
|  |  |  | 90 | 0 | 66.66
|  |  |  | 91 | 0 | 66.66
|  |  |  | 92 | 0 | 66.66
|  |  |  | 93 | 0 | 66.66
|  |  |  | 94 | 0 | 66.66
|  |  |  | 95 | 0 | 66.66
|  |  |  | 96 | 0 | 66.66
|  |  |  | 97 | 0 | 66.66
|  |  |  | 98 | 0 | 66.66
|  |  |  | 99 | 0 | 66.66
|  |  |  | 100 | 1 | 99.99
Use the 5th and 95th percentile for Dark Matter (Scope Creep) ranges in you Kanban Sim models.
Dark matter is work that is discovered during development. To the left enter in the Epic / Activity Name (or however you group smaller stories).
Some time before development the Epic or activity will be broken down into smaller stories. Enter that original number in the "Original # of Stories" Column. During development you may discover new stories, when this happens continue to group them under the Activity / Epic. Throughout the project update this spreadsheeet.
The distribution above is an experiment to see if it has any value.

## Project Buffer Usage
Week # | Date | Cumulative Completed Stories | Average WIP | Average Lead Time | % Complete | Projected Lead Time (Weeks) | Percent of Buffer Consumed | Total Bugeted Stories | 150
1 | 2015-03-06 | 0 | [5 empty] | Estimated Throughput (Week) | 7
2 | 2015-03-20 | 0 | 0 |  |  |  |  | Z-Curve Coefficient | 20%
3 | 2015-03-27 | 0 | 0 |  |  |  |  | Estimated % Failure | 50%
4 | 2015-04-03 | 0 | 0 |  |  |  |  | Estimated % Dark Matter | 100%
5 | 2015-04-10 | 0 | 0 |  |  |  |  | Project Buffer | 11
6 | 2015-04-17 | 0 | 0
7 | 2015-04-24 | 0 | 0
8 | 2015-05-01 | 0 | 0
9 | 2015-05-08 | 0 | 0
10 | 2015-05-15 | 0 | 0
11 | 2015-05-22 | 0 | 0
12 | 2015-05-29 | 0 | 0
13 | 2015-06-05 | 0 | 0
14 | 2015-06-12 | 0 | 0
15 | 2015-06-19 | 0 | 0
16 | 2015-07-10 | 0 | 0.064935
17 | 2015-07-17 | 1 | 0.073171 | 1.4 | 1 | 19.1333 | -19.39%
18 | 2015-07-24 | 1 | 0.068966 | 1.4 | 1 | 20.3 | -20.91%
19 | 2015-07-31 | 1 | 0.065217 | 1.4 | 1 | 21.4667 | -22.42%
20 | 2015-08-07 | 1 | 0.061856 | 1.4 | 1 | 22.6333 | -23.94%
21 | 2015-08-14 | 1 | 0.058824 | 1.4 | 1 | 23.8 | -25.45%
22 | 2015-08-21 | 1 | 0.056075 | 1.4 | 1 | 24.9667 | -26.97%
23 | 2015-08-28 | 1 | 0.053571 | 1.4 | 1 | 26.1333 | -28.48%
24 | 2015-09-04 | 1 | 0.051282 | 1.4 | 1 | 27.3 | -30%
25 | 2015-09-11 | 1 | 0.04918 | 1.4 | 1 | 28.4667 | -31.52%
26 | 2015-09-18 | 1 | 0.047244 | 1.4 | 1 | 29.6333 | -33.03%
Z-curve coefficient - This is the % of total project time spent on ramp up and ramp down.
Average Failure Demand - expressed as a percentage. This is the rate of failures in the system (bugs, tech debt, rework)
Average Dark Matter - expressed as a percentage. This is the rate of work expansion (scope creep, increased understanding).
Work in Progress, I want to understand this method more and possible disucss it with others

## Lookup Tables
Holidays
2015-06-20
2015-06-21
2015-06-22
2015-06-23
2015-06-24
2015-06-25
2015-06-26
2015-06-27
2015-06-28
2015-06-29
2015-06-30
2015-07-01
2015-07-02
2015-07-03